## Saranya M
Defect ID | Defect | Module | Severity | Priority | Defect Type | Description | Steps to Reproduce | Expected Result | Actual Result | Attachment | Tested By | Defect status | Status update by Tester
DEF001 | Incorrect error message displayed when deactivated user attempts to create account again | Platform | High | High | Functional | After a team member is deactivated by the admin, if the same user attempts to create/register an account again using the same email address, the system displays the error message “User email already exists.” The message is unclear and does not indicate that the account is already present but currently deactivated. A more informative message should be shown to help the user understand the actual account status. | 1.Login as Admin 2.Deactivate an existing team member account 3.Logout from admin account 4.Attempt to create/register a new account using the same deactivated email address 5.Observe the error message displayed | System should display a meaningful message such as: “This user account has been deactivated. Please contact the administrator.” or “An account with this email already exists and cannot be created again.” | System displays: “User email already exists.” | https://drive.google.com/file/d/1qvmG8Em7mJGmjBSix7FZWHxzkD5TAO_G/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF002 | Password Visibility Toggle (Eye Icon) Missing on Registration and Sign-In Page | Platform | High | High | UI | On the Sign-In page, the password field does not have an eye icon (visibility toggle) to show/hide the entered password. This impacts usability, as users cannot verify the password they have entered. | 1.Navigate to the Sign-In page 2.Enter a valid email 3.Click on the password field 4.Observe the password input area | An eye icon (visibility toggle) should be present in the password field to allow users to show/hide the password. | No eye icon is available in the password field. | https://drive.google.com/file/d/1T8mOAlm1GrVEnXUoCp75I2JHmNfrTUXv/view?usp=drive_link https://drive.google.com/file/d/19VvvOdkZZljJKg613yFRIlz3nO5aZIY-/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF003 | No Error Displayed When Reusing Old Password in Forgot Password Flow | Platform | High | High | Validation | When a user attempts to reset their password using the “Forgot Password” functionality and enters a password that has already been used previously, the system does not display any validation error | 1.Navigate to the Login page 2.Click on “Forgot Password” 3.Enter a registered email address and proceed 4.In the reset password screen, enter a previously used password as the new password 5.Submit the request | The system should display a validation error message such as: “New password cannot be the same as previously used passwords.” | No error message is displayed, and the system allows submission | Visibility toggle is not available to attach screenshot | Saranya | Done by shyam, open for review | Verified
DEF004 | Password reset link expires earlier than defined validity | Platform | High | High | Functional | The password reset link is displayed as valid for 1 hour, but in actual behavior, the link expires much earlier (within approximately 5–10 minutes). | 1.Go to Forgot Password 2.Enter registered email and request reset link 3.Open the reset email 4.Wait for 5–10 minutes 5.Click on the reset link | Reset link should remain valid for the full 1 hour as communicated | Reset link expires within 5–10 minutes | https://drive.google.com/file/d/1_Povtu2RCCVgm_ybJ7xXOSVlHP-7mYFI/view?usp=drive_link | Saranya | Done by shyam, open for review | The application should validate the reset token upon submission. If the token has expired, the password reset should be blocked, and the user should see an appropriate error message such as "Token Expired" or "Reset password link has expired. Please request a new link." | done by shyam, check it now
DEF005 | Application does not retain last visited module after reopening tab | Navigation/Session Management | High | High | Functional | When the application tab is closed and reopened, the user is always redirected to the Inbound Leads page, regardless of the last visited module (e.g., CRM, Campaigns). The system does not retain or restore the user’s previous navigation state. | 1.Login to the application 2.Navigate to Inbound Leads module 3.Close the browser tab 4.Reopen the application (login again if required) 5.Page retains in CRM or Campaign module. | User should be redirected to the last visited module | User is always redirected to Inbound Leads page | https://drive.google.com/file/d/14TBZ5x6kax3r_DPnxSRETH6HdZf-mNM0/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Still able to see Inbound Leads as lead page
DEF006 | Guide Assistant Conversation Messages Displayed in Incorrect Sequence | Ask AI(Guide Assistant) | Medium | Medium | Functional | During interactions in the Guide Assistant module, conversation messages are rendered in the wrong order. | 1.Open the Guide Assistant feature. 2.Initiate a new interaction. 3.Submit a user prompt or reply. 4.Review the message sequence in the chat window. | Messages should be displayed in proper conversational flow, with user input appearing before the related AI-generated response. | AI-generated messages are positioned ahead of the associated user response, reversing the intended sequence | https://drive.google.com/file/d/1CWaEcjZLNmfwryffb5lYLG6fNU3U1HdV/view?usp=drive_link | Saranya | Done by Santhosh, open for review Clear the conversion and try again. | Still Occurring
DEF007 | AI Chat fails to respond and returns 502 Bad Gateway error on message submission | AI Chat | High | High |  | When sending a message in the AI Chat interface, the request fails and the chat does not return any response. The frontend displays Failed to fetch, while the Network tab shows the API request returning a 502 Bad Gateway error. | 1.Open the AI Chat page: https://dev.intoleads.ai/ai/chat 2.Enter a prompt in the chat input field. Example: Find 20 CTOs at Series B fintech companies in London 3.Click Send or press Enter. 4.Observe the response | The AI assistant should process the request and return a response in the chat window. | Chat displays: Failed to fetch API request fails with: 502 Bad Gateway | https://drive.google.com/file/d/1PRkOFqROSjZ6IDwNqoLnhWTrt5OMDBI9/view?usp=drive_link | Saranya | verified by shankar, open for review | Verified
DEF008 | Selected AI Prediction details are not auto-focused after clicking a prediction card | AI Intelligence | High | High | UI | When a user clicks on a prediction card in the AI Predictions section, the corresponding prediction details are loaded below the page. However, the page does not automatically scroll or navigate to the details section. | 1.Login to the IntoLeads application. 2.Navigate to AI Intelligence module. 3.Open the Predictions tab. 4.Click on any prediction card (Example: EduSmart Learning Platform). 5.Observe the behavior after the prediction is selected. | After clicking a prediction card, the page should automatically scroll/focus to the selected prediction details section for better user experience. | The selected prediction details are displayed below the page, but the screen does not automatically navigate or scroll to the details section. User must manually scroll down to view the details.
DEF009 | Existing Details Are Auto-Filled When Creating a New Company | CRM>Companies | High | High | Functional | When creating a new Company Account, the form is automatically populated with previously entered or existing sequence details instead of opening with blank/default fields. | 1.Navigate to CRM>Companies module. 2.Click on + Add Company. 3.Observe the Create company. 4.Check the fields such as Name, Website, Industry | When creating a new sequence, all fields should be blank (or contain only default placeholders) so the user can enter fresh details. | The new sequence form displays pre-filled data such as existing sequence name, description, and email content. | https://drive.google.com/file/d/1RN-FoXdE8kvUzNdbZXUSWYIRJ0cQQIjY/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified | done by shyam, check it now
DEF010 | Encoded Characters Displayed in Company Search bar | CRM>Companies | High | High | UI | At the bottom of the Activities page, the pagination text displays encoded characters (\u00b7) instead of a proper separator symbol between page count and results count. | 1.Navigate to CRM → Companies page 2.Observe the Search bar. | Search Bar text should display correctly, for example: “Intoleads" | Search bar textbox is displayed as: “Search companies\u2026 results” | https://drive.google.com/file/d/1Xowz2thmqw5VvnjhGQO0prR8-SSpuw7y/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF011 | Duplicate Company Names,Contact,Oppotunities are Allowed Without Restriction | CRM>Companies | High | High | Validation | The system allows creation of multiple companies with the same or similar name without any validation or restriction. | 1.Navigate to CRM → Companies 2.Click on Add Company 3.Create a company with a name (e.g., Acme Cloud Solutions) 4.Save the company 5.Again, create another company with the same or similar name (e.g., acme cloud solutions) 6.Observe the company list | System should restrict duplicate company names OR Show a validation message/warning for existing similar names | Duplicate company names are created successfully without any warning or restriction | https://drive.google.com/file/d/1yKAAwLnezK8f5GuSVht_XoRZb9U56IdW/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified | done by shyam, check it now
DEF012 | Contact Association with Company Not Updated in Real Time | CRM>Companies | High | High |  | When contacts are added to a company, the company record does not immediately reflect the updated contact association. Instead, the contact count remains unchanged until the page is manually refreshed, | 1.Navigate to the CRM>Companies 2.Open any existing company record. 3.Add a new contact to the company. 4.Observe the contact count/status displayed in the company details. | The company should instantly display the newly added contact and update the contact count without requiring a page refresh. | The contact is not shown as associated immediately, and the contact count updates only after manually refreshing the page. | https://drive.google.com/file/d/1Ia1U31zZlyz1z9lIGKLfhczqoHfO6zSf/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified | done by shyam, check it now
DEF013 | Total Number of Companies Count Is Missing on Page | CRM>Companies | High | High | UI | The page does not display the total number of companies available/listed. This count is expected to provide users with quick visibility into the dataset size and overall records available. | 1.Navigate to the relevant companies listing page. 2.Observe the page header, summary section, or listing overview area. 3.Check for total companies count display. | The page should display the total number of companies for better visibility and tracking. | No total company count is shown on the page. | https://drive.google.com/file/d/1JXFBgNyH5eP9Gpruo33hSJ65hiLKMa2L/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Verified | done by shyam, check it now
DEF014 | Company Name Not Displayed in Contacts List After Selection During Contact Creation | CRM>Contacts | High | High | Functional | When creating a new contact and assigning an existing company, the selected company name is not displayed correctly in the Contacts list. | 1.Navigate to CRM>Contacts. 2.Click on Create Contact. 3.Fill in the required contact details. 4.Select or assign an existing company during contact creation. 5.Save the contact. 6.Check the Company column in the Contacts list. | The assigned company’s actual name should be displayed in the Company column. | The text “View Company” is displayed instead of the selected company name. | https://drive.google.com/file/d/1WLsjowcqyhv8ZO9BD0BOJmYCZvqM23V3/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Still not displayed
DEF015 | Bulk Import Accepts Mismatched Template File | CRM>Contacts | High | High | Validation | During bulk import, the system allows uploading and importing data even when the file format/template does not match the provided download template. This leads to incorrect or inconsistent data being imported. | 1.Navigate to Bulk Import section 2.Download the sample/template file 3.Modify the template structure (e.g., change column names/order or use a different format) 4.Upload the modified/mismatched file 5.Proceed with import | System should validate the uploaded file against the template and reject it if the format/structure does not match, displaying an appropriate error message. | System accepts and imports the mismatched file without validation. | https://drive.google.com/file/d/1VXrnjTrwYm9j6-kcFKegBUxNLm2OfZgX/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF016 | Company Records Remain Active After Imported Contact Removal | CRM>Contacts | High | High | Functional | When contacts are imported into the application, corresponding company records are automatically created in the Companies module. However, after deleting those imported contacts, the related company records still remain in the Companies module instead of being removed or handled accordingly. | 1.Navigate to Contacts module 2.Import contacts using bulk import option 3.Ensure new company names are included in the import file 4.Verify that corresponding companies are automatically created in Companies module 5.Delete the imported contacts 6.Navigate to Companies module 7.Check for the associated company records | Company records linked only to the deleted imported contacts should be automatically removed from the Companies module | Associated company records remain available in the Companies module even after deleting the imported contacts. | https://drive.google.com/file/d/1fqrmgfR0E18UebKOC5I3D94KFZEfJUmd/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF017 | Applied Filter Name Is Not Displayed Near Total Count in Contacts Module | CRM>Contacts | High | High | UI | In the Contacts module, when a filter is applied, the selected filter name/status is not displayed near the total records count section | 1.Navigate to the Contacts module 2.Apply any filter (example: status, source, owner, etc.) 3.Observe the total count section near the top of the page 4.Compare the behavior with other modules where filters are displayed beside the total count | The Contacts module should display the applied filter name/status near the total count similar to other modules for consistent UI behavior. | The applied filter name/status is not shown near the total count in the Contacts module. | https://drive.google.com/file/d/1eU3GsEXPcsbBBohHIwmeVnyUcNWd-Wn9/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Still Not Displayed
DEF018 | Unicode escape characters displayed in Delete Confirmation popup | CRM>Opportunity | High | High | UI | While attempting to delete an opportunity or activity, the confirmation popup displays Unicode escape characters (\u201c, \u201d) instead of proper quotation marks around the record name. | 1.Navigate to the Opportunities or Activities module. 2.Select any existing record. 3.Click on the Delete icon/action. 4.Observe the delete confirmation popup message. | The popup message should display the record name with proper quotation marks. Example: Delete “ClickBank - New Deal”? | The popup displays Unicode escape characters instead of proper quotation marks. Example: Delete \u201cClickBank - New Deal\u201d? | https://drive.google.com/file/d/1wNz8je4QPOXlNNLANhYvFqCqEA9HwUlS/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Verified
DEF019 | Proposal and Negotiation Stages Accept Past Dates from Previous Month | CRM>Opportunity | High | High | Functional | The application allows users to select and save a date from the previous month while updating the opportunity to the Proposal and Negotiation stages. | 1.Navigate to the Opportunities module. 2.Open an existing opportunity. 3.Change the stage to Proposal or Negotiation. 4.In the date field, select a date from the previous month. 5.Save the changes. | The system should validate the selected date and prevent users from choosing a date from the previous month. An appropriate validation message should be displayed. | The application accepts and saves the previous month's date for the Proposal and Negotiation stages without any validation. | https://drive.google.com/file/d/1ii-luhZmG-d-HASroWBgrF55G9-xloMD/view?usp=drive_link | Saranya | Open
DEF020 | Activity Logging Accepts Scheduled Date from Previous Month | CRM>Opportunity | High | High | Functional | While logging a new activity, the application allows users to select and save a scheduled date from the previous month | 1.Navigate to the Activities module. 2.Click Log Activity. 3.Enter the required activity details. 4.Select a scheduled date from the previous month. 5.Save the activity. | The system should not allow a scheduled date from the previous month and should display an appropriate validation message. | The application accepts and saves the activity with a scheduled date from the previous month. | https://drive.google.com/file/d/1OBb-DWYlnp8immveKvFD6lcUP9OC24Vf/view?usp=drive_link | Saranya | Open
DEF021 | Unable to Create New Activity When Date Is Selected | CRM>Activity | High | High | Functional | Users are unable to create a new activity after selecting or entering a date in the activity creation form. | Navigate to the Activities module Click on “Create New Activity” Fill in the mandatory fields Select or enter a date in the date field Click on Save/Create | Users should be able to successfully create a new activity with a valid date selected. | The activity is not created after selecting the date field. | https://drive.google.com/file/d/1f_qdvVHK4EVgbZWQuWoLOrkWJ1wr0Gh1/view?usp=drive_link | Saranya | Done by shankar, open for review | Verified
DEF022 | Form Builder: Full Name Field Is Not Reflected in Lead Source After Form Submission | Inbound Leads>From Builder | High | High | Functional | After embedding the generated form builder code into a webpage and submitting the form, the “Full Name” field value is not reflected or mapped correctly in the Lead Source/created lead record | 1.Navigate to Form Builder module 2.Create a form with a “Full Name” field 3.Generate and embed the form code into a webpage 4.Open the embedded form 5.Enter valid details including Full Name 6.Submit the form 7.Check the created lead/source details in the application | The Full Name entered in the embedded form should be captured and displayed correctly in the corresponding lead/source record. | The Full Name value entered in the form is not reflected in the lead source/created lead record. | https://drive.google.com/file/d/1Xpf8fe6kyNFH2JHn1-CTh_vA6adGEXCh/view?usp=drive_link | Saranya | Done by shyam, open for review | Website has Raghav's access alone once the website is live will retest
DEF023 | Website: Blank Page Displayed After Form Submission Without Success Confirmation Message | Inbound Leads>From Builder | High | High | Functional | After submitting the form on the website, the page becomes blank/empty and no success confirmation message is displayed to the user | 1.Open the embedded website form 2.Enter valid form details 3.Click on Submit 4.Observe the page behavior after submission | After successful form submission, the user should be redirected appropriately or shown a success confirmation message indicating the form was submitted successfully. | The page becomes blank/empty after form submission and no success or confirmation message is shown. | https://drive.google.com/file/d/1Xpf8fe6kyNFH2JHn1-CTh_vA6adGEXCh/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF024 | Inventory Catalog Upload Shows Success Message but Catalog History Displays Error Status | Inbound Leads>Inventory | High | High | Functional | While uploading a CSV file into the Inventory Catalog module, the application displays a success message stating that the catalog was uploaded successfully and parsing is being processed in the background. However, under the Catalog History section, the uploaded file status is shown as “Error.” | 1.Navigate to Inventory Catalog module 2.Upload a valid CSV file 3.Observe the success toast/message after upload 4.Navigate to Catalog History section 5.Check the status of the uploaded catalog | The upload status displayed in Catalog History should match the actual upload/parsing result. If parsing fails, a proper error message should be shown instead of a success notification. | A success message is displayed stating the catalog upload was successful and parsing is in progress, but the Catalog History section shows the upload status as “Error.” | https://drive.google.com/file/d/1xy88VupKTGVz_F6b6obm_A02qNQSoQQ2/view?usp=drive_link | Saranya | Done by shyam, open for review | Partially Verified Thank You message appears twice | done by shyam, check it now
DEF025 | Inventory Catalog Upload Error Message Does Not Provide Clear Failure Information | Inbound Leads>Inventory | High | High |  | When uploading a CSV file into the Inventory Catalog module, the upload process fails and an error status is shown in Catalog History. However, the displayed error message does not provide clear or meaningful information about the actual cause of the failure. | 1.Navigate to Inventory Catalog module 2.Upload a CSV file 3.Wait for the parsing process to complete 4.Navigate to Catalog History 5.Observe the error message displayed for the failed upload | The application should display a clear and meaningful error message specifying the exact issue with the uploaded CSV file or parsing process. | The system displays a generic or unclear error message without sufficient details about the failure reason. | https://drive.google.com/file/d/1xy88VupKTGVz_F6b6obm_A02qNQSoQQ2/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF026 | Duplicate Records Are Displayed During Research Intelligence Processing | Intelligence>Research Intelligence | High | High |  | While performing Research Intelligence operations, duplicate records/items are displayed in the results. The system does not properly prevent or handle duplicate entries during the intelligence generation process, leading to repeated data visibility. | 1.Navigate to Intelligence>Research Intelligence module 2.Perform a research intelligence operation/search 3.Wait for the results to load/process 4.Observe the generated/displayed records | The system should prevent duplicate entries and display only unique records in the Research Intelligence results. | Duplicate records are displayed in the Research Intelligence results. | https://drive.google.com/file/d/1IDs-r_6VooGq_DK0KKhMFFH-udKTbbfm/view?usp=drive_link | Saranya | Open
DEF027 | Next Context” button remains non-functional after audience type selection in Campaign workflow | Outbound>Campaigns | High | High | Functional | In the Campaigns module, during the audience addition workflow, the campaign updates successfully after selecting the next audience. However, upon selecting the audience type, the “Next Context” button remains inactive/non-functional and does not navigate to the subsequent step. | 1.Login to the application 2.Navigate to Campaigns 3.Create a new campaign or open an existing campaign 4.Click on “Add Audience” 5.Select an audience and proceed to the next audience step 6.Choose an audience type 7.Click on the “Next Context” button 8.Observe the behavior | The “Next Context” button should be enabled and navigate the user to the next workflow step after valid audience type selection. | The “Next Context” button remains non-responsive after selecting the audience type. | https://drive.google.com/file/d/12G969iUiyGe_YCfSjEdY-6Ani8J5eSrw/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF028 | Campaign Stuck in “Sending” Status Even After Completion (Created Previous Day) | Outbound>Campaigns | High | High | Functional | An email campaign remains in the “Sending” status even after a significant time (over a day since creation). The campaign does not transition to a final state such as “Sent” or “Completed,” indicating a possible issue with status updates or backend processing. | 1.Navigate to Outbound → Campaigns 2.Create and send an email campaign 3.Wait for the campaign to process (several hours or more) 4.Revisit the campaigns dashboard 5.Observe the campaign status | Campaign status should update from “Sending” to: “Sent” / “Completed” once all emails are processed Or “Failed” if any issue occurs | Campaign continues to display “Sending” even after a long duration (e.g., 1 day) | https://drive.google.com/file/d/1RVODlZ0rkZ0y82mjpfcdV1cx6VfjFGLE/view?usp=drive_link | Saranya | Done by Santhosh, open for review Campagin page is discarded. | 404 error occurs to test this
DEF029 | Email Preview Panel Displays Blank Content Instead of Rendered Email Body | Outbound>Campaigns | High | High | UI | The Email Preview panel appears almost empty and displays only the user name (“Saranya M”) while the actual email body/content is not rendered | 1.Navigate to the Email/Campaign module 2.Create or select an email template 3.Open the Email Preview panel 4.Observe the rendered preview content | The complete email template content, including body text, formatting, and dynamic fields, should render properly in the Email Preview panel. | The Email Preview panel appears blank or partially empty, displaying only the user name while the actual email body/content is missing. | https://drive.google.com/file/d/1V0Eoew7NS4zgzO1xf_Ob3YKz7zBry6QN/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF030 | Email campaign performance metrics display 0% even after email is opened | Outbound>Campaigns | High | High | Functional | In the Email Campaigns module, even after the recipient successfully opens and reads the email, the campaign performance metrics continue to display 0% open rate. The email open activity is not being reflected in the campaign analytics/performance tracking. | 1.Login to the application 2.Navigate to Email Campaigns 3.Create and send an email campaign to a valid recipient 4.Open the received email from the recipient inbox 5.Return to the Email Campaigns performance/analytics section 6.Observe the open rate and performance metrics | The campaign analytics should track the email open activity and update the performance metrics/open rate accordingly. | Performance metrics continue to display 0% even after the email has been opened and read. | https://drive.google.com/file/d/1G_bMNFgNN0l6Y_IXukKW4lPboRvYlcOd/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF031 | Back button intermittently throws an error after creating Identity/Audience or Content | Outbound>Campaigns | High | High |  | An error occurs when the user clicks the Back button after completing Identity and Audience creation, or sometimes after creating Content. The issue appears intermittently and disrupts navigation within the flow. | 1.Log in to Intoleads 2.Navigate to campaign creation 3.Create Identity and Audience 4.(Optional) Proceed to create Content 5.Click on the Back button | User should be navigated back to the previous step without any error | An error is displayed OR Page does not load correctly / breaks | https://drive.google.com/file/d/1rgUL2duID31j24AmCRM8FtOny9ZiT8QF/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF032 | Estimated recipient count does not match selected audience when Smart Filter is applied | Outbound>Campaigns | High | High |  | When an audience is created and the Smart Filter option is selected, the estimated recipient count shown does not match the actual audience count displayed in the Review step | 1.Log in to Intoleads 2.Navigate to campaign creation 3.Create an Audience with defined criteria 4.Enable/select Smart Filter 5.Proceed to the Review step 6.Compare: 7.Estimated recipient count 8.Actual audience count shown | Estimated recipient count should accurately reflect the audience selected | Estimated recipient count differs from the audience count in Review | https://drive.google.com/file/d/1W3ugSfI42PpKifOm1hX86_wWYTFReqy0/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF033 | Recipient list not visible after audience creation and in Review step | Outbound>Campaigns | High | High |  | After creating an audience, the estimated recipients list is not displayed. The same issue persists in the Review step, where the recipient list should be visible for confirmation | 1.Log in to Intoleads 2.Navigate to campaign creation 3.Create an Audience with valid criteria 4.Proceed to the next steps 5.Check for recipient list visibility 6.Navigate to the Review step | Recipient list should be visible after audience creation Same list should be available in Review for final confirmation | Recipient list is not displayed after audience creation Recipient list is also missing in the Review step | https://drive.google.com/file/d/1W3ugSfI42PpKifOm1hX86_wWYTFReqy0/view?usp=drive_link | Saranya | Campagin page is Discarded. | Still could see the UI
DEF034 | Scheduled email is sent immediately instead of selected time | Outbound>Campaigns | High | High |  | When a user schedules an email by selecting a future date/time, the email is sent immediately instead of being delivered at the chosen time. This breaks the expected scheduling functionality. | 1.Log in to Intoleads 2.Create a campaign and proceed to email setup 3.Choose Schedule Send option 4.Select a future date and time 5.Confirm and trigger the send | Email should be sent at the exact scheduled date and time chosen by the user | Email is sent instantly Selected scheduled time is ignored |  | Saranya | Campagin page is Discarded. | Still could see the UI
DEF035 | Data Synchronization Failure in Data Gaps Module for CRM-Populated Fields | Settings>Data Gaps | High | High |  | The Data Gaps module is not fetching or displaying CRM-populated information such as industry, email details, and uploaded documents. Although these fields are available in the CRM, they are missing in the Data Gaps workflow, indicating a synchronization or mapping issue. | 1.Navigate to CRM and create or update records with populated fields such as industry, email, and uploaded documents. 2.Save the record successfully. 3.Navigate to the Data Gaps module. 4.Search for or open the corresponding record. | All relevant CRM-populated data fields should be fetched and displayed accurately in the Data Gaps module. | Industry, email, and uploaded document information are missing and not reflected in the Data Gaps module. | https://drive.google.com/file/d/19CFwGAkUix93GXQV_R5wntR1pAhjMJgg/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF036 | Selected File Name Remains in Upload Field After Failed Upload Attempt | Settings>Document | High | High |  | When a file upload fails, the selected file name continues to remain displayed in the Choose File field instead of being cleared/reset. | 1.Navigate to Settings → Documents. 2.Select a file for upload. 3.Trigger an upload failure (e.g., unsupported file behavior / API rejection). 4.Observe the Choose File field after the failure. | The file input should reset after a failed upload attempt, and the Choose File field should return to its default empty state. | The previously selected file name remains visible in the upload field even after the upload fails. | https://drive.google.com/file/d/1zP1U4IARvX4JBU3LBqmU_-syhB7wz0iS/view?usp=drive_link | Saranya | Done by shyam, open for review | Verified
DEF037 | Markdown (.md) File Upload Fails Despite Being Listed as Supported Format | Settings>Document | High | High | Functional | The system displays Markdown (.md) as a supported upload format in the Documents section. However, when attempting to upload a markdown file, the request fails and returns a 400 Bad Request response, preventing the file from being uploaded successfully. | 1.Navigate to Settings → Documents. I2.n the upload section, confirm that Markdown is listed as a supported file type. 3.Select Markdown (.md) as the file to upload. 4.Fill required fields such as category/description if applicable. 5.Attempt to upload the file. Observe the network/API response. | Since Markdown is listed as a supported format, the system should successfully accept and process .md files without errors. | The upload request fails with 400 Bad Request, and the markdown file is not uploaded successfully. | https://drive.google.com/file/d/1zP1U4IARvX4JBU3LBqmU_-syhB7wz0iS/view?usp=drive_link | Saranya | Verified by shankar - working fine | Verified
DEF038 | Duplicate Documents Are Uploaded Multiple Times | Settings>Document | High | High | Validation | The system allows the same document/file to be uploaded multiple times, resulting in duplicate document entries. | 1.Navigate to the Documents/File Upload module 2.Upload a document successfully 3.Attempt to upload the same document again 4.Check the uploaded documents list | The system should either prevent duplicate document uploads or notify the user that the document already exists. | The same document is uploaded and stored multiple times as duplicate entries. | https://drive.google.com/file/d/1zP1U4IARvX4JBU3LBqmU_-syhB7wz0iS/view?usp=drive_link | Saranya | Done by shankar, open for review | Verified
DEF039 | Document remains stuck in “Processing” state after upload | Settings>Document | High | High | Functional | After uploading a document successfully, the document status remains in the “Processing” state for a long time and does not move to a completed/success state. | 1.Login to the application 2.Navigate to the document upload module/page 3.Upload a valid document 4.Wait for the upload and processing to complete 5.Observe the document status | The document status should update from “Processing” to a final state such as “Completed”, “Uploaded”, or “Success” once processing is finished. | The document remains indefinitely in the “Processing” state even after sufficient wait time. | https://drive.google.com/file/d/1zP1U4IARvX4JBU3LBqmU_-syhB7wz0iS/view?usp=drive_link | Saranya | Done by Shyam, open for review | Verified | done by shyam, check it now
DEF040 | "Schedule a Demo" Link in Email Chat Does Not Redirect to Application | Email>Inbox | High | High | Functional | When a user opens an email conversation in the Email Inbox and clicks the "Schedule a demo" hyperlink displayed within the email content, the application does not redirect the user to the intended demo scheduling page or any relevant application screen. | 1.Navigate to Email → Inbox. 2.Open an email containing the "Schedule a demo" link. 3.Click on the "Schedule a demo" hyperlink. | User should be redirected to the designated demo scheduling page or relevant application module. The hyperlink should function correctly and allow users to proceed with demo booking. | Clicking the "Schedule a demo" hyperlink does not redirect the user anywhere. No page navigation or action is triggered. | https://drive.google.com/file/d/1AfTDtX4WO4J0I1_ZYE11icZbEz18XMCz/view?usp=drive_link | Saranya | Open, Santhosh - I checked this, it comes from AI, It is prompt thing, not a error. | Verified
DEF041 | Emails Sent via Email Chat Are Delivered to Spam Folder in External Email Providers (Gmail, Yahoo, etc.) | Email>Inbox | High | High | Functional | Emails sent through the application's Email Chat feature are being delivered to the Spam/Junk folder when received by external email providers such as Gmail, Yahoo, and other public email services. Instead of reaching the recipient's primary inbox, the emails are flagged as spam, affecting email visibility and communication effectiveness. | 1.Navigate to Email → Email Chat. 2.Compose and send an email to an external email address (e.g., Gmail or Yahoo). 3.Log in to the recipient's mailbox. 4.Check the Inbox and Spam/Junk folders. | Emails sent via Email Chat should be delivered to the recipient's primary inbox. Emails should not be flagged as spam by external email providers. | Emails sent via Email Chat are delivered to the Spam/Junk folder in Gmail, Yahoo, and other external email services. | https://drive.google.com/file/d/1iDB4Iptuw7T12v4kAJZQ3oehRe0zF8R_/view?usp=drive_link | Saranya | Open, Santhosh - I checked this, it comes from AI, It is prompt thing, not a error. | Verified
DEF042 | Empty Dialog Box Appears When Clicking the Three-Dot (⋮) Menu in Lead Enrollments | Email>Automation | High | High |  | In the Lead Enrollments section under Email Automation, clicking the three-dot (⋮) action menu for an enrolled lead displays an empty dialog/popup with no menu options or actionable items. The dialog appears blank, causing confusion and preventing users from accessing any intended actions. | 1.Navigate to Email → Automation. 2.Open the Enrollments tab. 3.Locate any enrolled lead record. 4.Click the three-dot (⋮) menu on the right side of the row. | A dropdown/menu should display the available actions (e.g., View Details, Pause, Resume, Remove Enrollment, etc.). | An empty dialog/popup is displayed when clicking the three-dot menu. No actions or menu items are visible. | https://drive.google.com/file/d/1EQ9iFi4qO0FDJywWnKp7Ko9HbNrqDwsY/view?usp=drive_link | Saranya | Done by Santhosh, open for review | Verified
DEF043 | Bottom Profile Section Overlaps Left Navigation Menu | Intelligence | High | High | UI | The user profile section is fixed at the bottom of the left navigation panel and overlaps with the sidebar menu content. | 1.Login to IntoLeads. 2.Navigate to Intelligence. 3.Observe the left navigation panel containing Intelligence menu items. 4.Scroll or view the lower portion of the sidebar. | The sidebar menu and profile section should be properly spaced. All navigation items should remain visible and accessible without being obscured by the profile section. | The fixed profile section at the bottom overlaps the sidebar navigation area, potentially hiding or obstructing menu items and creating a cluttered UI. | https://drive.google.com/file/d/1Wm2mGe1FX1aNDW1Z-eI0r5W52PaPELqI/view?usp=drive_link | Saranya | Open
DEF044 | User Profile Information is Displayed Twice in Account Section | User Profile | High | High | UI | When the user clicks on the account/profile section, the user's information (Name, Email Address, and Role) is displayed in both the profile dropdown and the profile card section simultaneously. This results in duplicate information being shown on the screen, creating visual clutter and a confusing user experience. | 1.Login to the IntoLeads application. 2.Navigate to the AI Chat module. 3.Click on the user profile/account section at the bottom-left corner. 4.Observe the displayed user information. | User details (Name, Email, and Role) should be displayed only once within the account/profile section. | User details are displayed twice—once in the profile dropdown and again in the profile card area. | https://drive.google.com/file/d/1zzIsC2_v1n_POZEkYMim0yczmSjmC7i1/view?usp=drive_link | Saranya | Done by Shyam, open for review | Verified
DEF045 | Expiration Date and Sent Date Are Not Updated Immediately After Resending Invitation | Tools>Team>Pending Invitations | Low | Medium | Functional | When a pending invitation is resent, the invitation's Expiration Date and Sent Date are not updated immediately in the UI. The updated expiration date is only reflected after manually refreshing the page, and the Sent Date continues to display the old date instead of the current resend date. | 1.Login to the IntoLeads application as an Admin. 2.Navigate to Team Management. 3.Go to the Pending Invitations section. 4.Select a pending invitation. 5.Click Resend Invitation. 6.Observe the Sent Date and Expiration Date displayed in the invitation list. 7.Refresh the page and observe the dates again. | Upon resending an invitation, both the Sent Date and Expiration Date should update immediately without requiring a page refresh. | The Expiration Date does not update immediately after resending and only reflects the new value after a manual page refresh. The Sent Date remains unchanged and continues to display the previous date even after the invitation is resent. | https://drive.google.com/file/d/1tDXge6CjQgzauGmxiGMHMZs-zh5bMVo9/view?usp=drive_link | Saranya | Done by Shyam, open for review | Verified
DEF046 | Back Navigation from New Campaign Page Results in 404 Error When Accessed via Contacts Email Action | Contacts>Email Campaigns | Low | Medium | Functional | When initiating an email campaign from the Contacts module, the user is redirected to the New Campaign page. If the user attempts to navigate back using the application's back navigation option (or browser back button), a 404 Error page is displayed instead of returning to the previous Email Campaign or Contacts page. This breaks the navigation flow and negatively impacts the user experience. | 1.Login to the IntoLeads application. 2.Navigate to the Contacts module. 3.Select one or more contacts. 4.Choose the option to send an email/create an email campaign. 5.Verify that the user is redirected to the New Campaign page. 6.Click the Back button (application back button or browser back button). 7.Observe the resulting page. | The user should be navigated back to the previous page (Contacts list or Email Campaign page) without any errors. | A 404 Error page is displayed when navigating back from the New Campaign page. | https://drive.google.com/file/d/1qZ730Yu95E9vLNS0FVVrHfluW6W9s-bn/view?usp=drive_link | Saranya | Done by Santhosh, open for review. I removed the button. | Still Occurs
DEF047 | New Chat Displays 404 Error with "An Unexpected Error Occurred. Please Try Again." Message | New Chat | High | High | Functional | While performing a New Chat operation in the AI Chat module, the application fails to create a new conversation and displays a 404 error along with the message: "An unexpected error occurred. Please try again." | 1.Log in to the application. 2.Navigate to the AI Chat module. 3.Click on New Chat. 4.Observe the response. | A new chat session should be created successfully, and the user should be redirected to the new conversation without any errors. | A 404 error is displayed with the message "An unexpected error occurred. Please try again.", and the new chat is not created. | https://drive.google.com/file/d/1rLYuerQrzQTNQFtDuhDIwEjkouJH2zzS/view?usp=drive_link | Saranya | Open
DEF048 | Allow Sequence Dates to Be Updated Individually for User Convenience | Email>Automation>Sequence | High | High | Functional | Currently, sequence steps are created with randomly assigned dates, making it difficult for users to organize and schedule their outreach effectively. To improve usability, users should be able to update the scheduled date of each sequence step individually after the sequence is created. | 1.Log in to the application. 2.Navigate to the Sequences module. 3.Create a new sequence with multiple steps. 4.Save the sequence. 5.Open the created sequence and try to modify the scheduled date of any individual step. | Users should be able to edit and update the scheduled date for each sequence step after the sequence is created. | The dates are assigned during sequence creation and cannot be updated individually, making it difficult for users to adjust the schedule based on their requirements. | https://drive.google.com/file/d/1vwYB6AbIBo9vZrwGQf_p5-V1nszbJIQF/view?usp=drive_link | Saranya | Open
DEF049 | Popup Dialog Box Does Not Have a Close Button | App | Medium | Medium | UI | The popup dialog box displayed in the application does not include a Close (X) button. Users must rely on alternative methods (if available) to dismiss the popup, which affects usability and user experience. | 1.Log in to the application. 2.Navigate to the relevant module. 3.Perform the action that opens the popup dialog. 4.Observe the popup. | The popup dialog should display a Close (X) button, allowing users to dismiss it easily. | The popup dialog does not contain a Close (X) button, making it inconvenient for users to close the dialog. | https://drive.google.com/file/d/10GSMYK0PRNkotZwfSeDi7M-KZKwY14p0/view?usp=drive_link | Saranya | Open
DEF050 | URL Slug Not Updating Beyond First Character | Inbound Leads-Forms | Medium | High | Functional | While entering text in the "Name" field, the URL slug is generated using only the first character and does not update further as the user continues typing | 1. Go to Inbound Leads 2. Open the forms page 3. Click on "+New Form" 4. Locate the "Name" input field 5. Start typing a name (e.g., "Arvi") 6. Observe the URL slug field | URL slug should dynamically update based on the full input (e.g.. "arvi") | URL slug updates only with the first character (e.g., "a") and does not change further | https://drive.google.com/file/d/17BcNtnixXroWL7NcNL-fu1XgGHpAGyLh/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF051 | UI Misalignment When Zooming Page | Inbound Leads-Forms | Medium | High | UI | When the user zooms the webpage using browser zoom (Ctrl + + / Ctrl + -), the form layout breaks. Input fields, labels, and buttons become misaligned, affecting usability | 1. Go to Inbound Leads 2. Open the forms page 3. Press Ctrl + + to zoom in (or Ctrl + - to zoom out) 4. Observe form layout | The form UI should remain responsive and properly aligned at all zoom levels | Form elements become misaligned, overlap, or shift out of position when zoom is applied | https://drive.google.com/file/d/1lT6s6RgJ4vS_uytNsZV9XBscV931QzVG/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF052 | Negative values displayed in Goal metrics (Submissions & Conversions | Inbound Leads-Campaigns | Medium | High | Functional | The Goal metrics section is displaying negative values for Submissions and Conversions, which is logically incorrect for these metrics. These values should represent counts and must not be negative | 1. Go to Inbound Leads 2. Open Campaigns 3. Click on "+New Campaign" 4. Enter Negative Value in Goal: Submissions Field and Goal: Coversions Field | Submissions and Conversions should display values as 0 or positive integers | Negative values are displayed (e.g., -1 for Submissions, -2200 for Conversions) | https://drive.google.com/file/d/17Li7J-aNuufKljRszyNle91Pcwzi9wXI/view?usp=drive_link | Aravinda Swamy | Open
DEF053 | Star rating not clickable in Live Preview form | Inbound Leads-Form Builder | Medium | Medium | Functional | In the Live Preview section, the star rating input under "How did you hear about us?" is not interactive. Users are unable to click or select any rating value | 1. Go to Inbound Leads 2. Open the form builder 3. Select Rating Field 4. Navigate to Preview 5. Locate the question "How did you hear about us?" 6. Try clicking on the star rating | User should be able to click on stars to select a rating | Stars are not clickable and no rating can be selected | https://drive.google.com/file/d/1kgthSRSd9xWj93TgXuIzENFE05TFj-3I/view?usp=drive_link | Aravinda Swamy | Open
DEF054 | Delete count not updating based on applied filter | Inbound Leads-Leads | High | High | Functional | When a filter is applied, the Total count updates correctly based on the filtered data. However, the Delete count does not update accordingly and continues to reflect the previous/unfiltered count, leading to incorrect data display | 1. Go to Inbound Leads 2. Open Leads 3. Click on Checkbox 4. Observe initial Total and Delete counts (e.g., Total = 8, Delete = 8) 5.Apply a filter 6.Observe updated Total count (e.g., Total = 2) 7. Check Delete count | Delete count should update according to the applied filter (e.g., Delete = 2) | Delete count does not update correctly and shows incorrect value (e.g., 6 instead of 2) | https://drive.google.com/file/d/1zrc_1pMNYvZki6DgRRrwEDdSn_Ok9rkb/view?usp=drive_link | Aravinda Swamy | Open
DEF055 | Duplicate company leads can be created | CRM-Companies | High | High | Functional | The system allows creating duplicate company leads with the same details (e.g. company name, Webiste and Industry). This leads to data duplication and affects data accuracy | 1. Go to CRM 2. Open Companies 3. Navigate to Add Company 4. Enter lead details (e.g., same company name, Webiste ) Submit the form 5. Repeat with the same details | System should prevent duplicate entries or show a validation message | Duplicate company leads are created successfully without any warning |  | Aravinda Swamy | Done by Shankar, Open for Review | Verified
DEF056 | A–Z and Z–A sorting not working correctly in Name filter | CRM-Companies | Medium | High | Functional | The sorting functionality using A–Z and Z–A options is not working as expected. The data is either not sorted correctly or does not change after applying the sort option | 1. Go to CRM 2. Open Companies 3. Apply Name sorting filter (A–Z) 4. Observe the order of records 5. Apply Name sorting filter (Z–A) 6. Observe the order again | A–Z: Data should be sorted in ascending alphabetical order and Z–A: Data should be sorted in descending alphabetical order | Sorting does not work correctly / data remains unsorted or incorrectly ordered | https://drive.google.com/file/d/1_aLpzgUeQEu4Fce9vvNXroqvXFcg28_l/view?usp=drive_link | Aravinda Swamy | Open
DEF057 | Input fields showing prefilled sample data instead of placeholder text | CRM-Companies | Medium | High | UI | The input fields in the Add Company form display sample company data (e.g., "Acme Corp", "https://acme.com ") instead of placeholder text. This may confuse users into thinking the fields are prefilled | 1. Go to CRM 2. Open Companies 3. Navigate to Add Company form 4. Observe the input fields (Name, Website, etc.) | Fields should display placeholder text such as: "Enter Name" "Enter Website" "Enter Industry" | Fields display sample data like "Acme Corp" and "https://acme.com " | https://drive.google.com/file/d/1Gfc1RItaqmsa7mgyGfPwg-7Hl6H2ra_R/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF058 | Bulk upload “Drop CSV or click to browse” option not accessible via keyboard | CRM-Contacts | High | High | Accessibility | The bulk upload area (“Drop CSV here or click to browse”) is not accessible using the keyboard. Users cannot trigger the file upload dialog using Enter or Space keys, making the feature inaccessible without a mouse | 1.Navigate to Bulk Upload section 2.Use Tab key to focus on upload area 3.Press Enter or Space 4.Observe behavior | File upload dialog should open when pressing Enter/Space on the upload area | No action occurs upload dialog does not open via keyboard | https://drive.google.com/file/d/1oY8AjngdD8Fnph6TUkxcdRE9SsR7smFj/view?usp=drive_link | Aravinda Swamy | Open
DEF059 | Mandatory field indicators not displayed for required fields | CRM-Contacts | Medium | High | UI | Required fields such as First Name and Last Name do not display any mandatory indicator (e.g., *). This makes it unclear to users which fields are required before form submission | 1. Go to CRM 2. Open Contacts 3. Click on "+ Add Contact" 4. Observe labels for required fields (First Name, Last Name) | Required fields should be clearly marked with an indicator (e.g... * or “Required”) | No mandatory indicator is shown, even though validation errors appear | https://drive.google.com/file/d/1ovj03u2qjNStnRmUaHw1BQbci75JIBFA/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Still Not Displayed
DEF060 | Mandatory field indicators not displayed for required field | Tools-Team | Medium | High | UI | Required fields such as Email do not display any mandatory indicator (e.g., *). This makes it unclear to users which fields are required before form submission | 1. Go to Tools 2. Open Team 3. Click on "+ Invite Member" 4. Observe labels for required field (Email) | Required field should be clearly marked with an indicator (e.g... * or “Required”) | No mandatory indicator is shown, even though validation errors appear | https://drive.google.com/file/d/1NjESo3W9dVQrRzs4FN08fNqjaBQfXnsi/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF061 | Mandatory field indicators not displayed for required field | CRM-Activities | Medium | High | UI | Required fields such as Subject do not display any mandatory indicator (e.g., *). This makes it unclear to users which fields are required before form submission | 1. Go to CRM 2. Open Activities 3. Click on "+ Log Activity" 4. Observe labels for required field (Subject) | Required field should be clearly marked with an indicator (e.g... * or “Required”) | No mandatory indicator is shown, even though validation errors appear | https://drive.google.com/file/d/1L5thX_XQZkNb5Gx3mqoTH3fg9Qt_IcG3/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF062 | Negative values allowed in Avg Sales Cycle field | Settings-Account | Medium | High | Validation | The "Avg Sales Cycle (days)" field allows users to enter or select negative values, which is logically incorrect for a duration field | 1. Go to Settings 2. Open Account 3. Locate "Avg Sales Cycle (days)" field 4. Use arrow keys or manually enter a negative value (e.g. -1) | Field should restrict input to non-negative values | Field accepts negative values | https://drive.google.com/file/d/1SBxv3TwFi4kvfikJi0MB7c549IyPyHQY/view?usp=drive_link | Aravinda Swamy | Open
DEF063 | Negative values allowed in Avg Deal Size field | Settings-Account | Medium | High | Validation | The "Avg Deal Size" field allows users to enter or select negative values, which is logically incorrect for a duration field | 1. Go to Settings 2. Open Account 3. Locate "Avg Deal Size" field 4. Use arrow keys or manually enter a negative value (e.g. -0.01) | Field should restrict input to non-negative values | Field accepts negative values | https://drive.google.com/file/d/1SBxv3TwFi4kvfikJi0MB7c549IyPyHQY/view?usp=drive_link | Aravinda Swamy | Open
DEF064 | Delete count not updating based on applied filter | CRM-Contacts | High | Medium | Functional | When a filter is applied, the Total count updates correctly based on the filtered data. However, the Delete count does not update accordingly and continues to reflect the previous/unfiltered count, leading to incorrect data display | 1. Go to CRM 2. Open Contacts 3. Click on Checkbox 4. Observe initial Total and Delete counts (e.g., Total = 50, Delete = 50) 5.Apply a any filter 6.Observe updated Total count (e.g., Total = 2) 7. Check Delete count | Delete count should update according to the applied filter (e.g., Delete = 2) | Delete count does not update correctly and shows incorrect value (e.g., 48 instead of 2) | https://drive.google.com/file/d/1jahAlg43Gp_4KjjQ0cihnEpy8D5tR9xr/view?usp=drive_link | Aravinda Swamy | Open
DEF065 | Delete count not updating based on applied filter | CRM-Opportunities | High | Medium | Functional | When a filter is applied, the Total count updates correctly based on the filtered data. However, the Delete count does not update accordingly and continues to reflect the previous/unfiltered count, leading to incorrect data display | 1. Go to CRM 2. Open Opportunities 3. Click on Checkbox 4. Observe initial Total and Delete counts 5.Apply a any filter 6.Observe updated Total count 7. Check Delete count | Delete count should update according to the applied filter | Delete count does not update correctly and shows incorrect value | https://drive.google.com/file/d/1AGnvWlnzeob9-Ppd0aILHoqfN_gvOotU/view?usp=drive_link | Aravinda Swamy | Open
DEF066 | Delete count not updating based on applied filter | CRM-Activities | High | Medium | Functional | When a filter is applied, the Total count updates correctly based on the filtered data. However, the Delete count does not update accordingly and continues to reflect the previous/unfiltered count, leading to incorrect data display | 1. Go to CRM 2. Open Activites 3. Click on Checkbox 4. Observe initial Total and Delete counts 5.Apply a any filter 6.Observe updated Total count 7. Check Delete count | Delete count should update according to the applied filter | Delete count does not update correctly and shows incorrect value | https://drive.google.com/file/d/1BEnuo8FGco_12LR30QF5BsuzqL5fDwYh/view?usp=drive_link | Aravinda Swamy | Open
DEF067 | Filtering by company (“Alphabet”) leaves empty gaps between rows in the Company column | CRM-Contacts | Medium | Medium | UI | Filtering by company (“Alphabet”) leaves empty gaps between rows in the Company column | 1. Go to CRM 2. Click on Contacts 3. Click on Company Filter arrow symbol 4. Observe the filter data | Filtered records should appear continuously without blank spaces | Large empty row gaps remain after filter is applied | https://drive.google.com/file/d/1RhqaIW_wYEFZLsT6xM6W10ztdqXf8s-y/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF068 | Mandatory field indicators not displayed for required fields | CRM-Opportunities | Medium | Medium | UI | Required fields such as Name do not display any mandatory indicator (e.g., *). This makes it unclear to users which fields are required before form submission | 1. Go to CRM 2. Open Opportunity 3. Click on "+ New Opportunity" 4. Observe labels for required fields (Name) | Required fields should be clearly marked with an indicator (e.g... * or “Required”) | No mandatory indicator is shown, even though validation errors appear | https://drive.google.com/file/d/1l9mBO2aThjtbc6l3PguhywXdfPWi87n5/view?usp=drive_link | Aravinda Swamy | Done by Ravi, Open for Review | Verified
DEF069 | Contacts are associated with the wrong company after Bulk Import in Company profile | CRM-Companies-Bulk import | High | High | Functional | After performing a bulk import of contacts using a CSV file, the system automatically creates a new company when a different company name is found in the import file. However, the contacts related to the newly created company are still associated with the previously existing company instead of the correct one | 1.Create a company named “Aravind Industries.” 2.Navigate to the company profile. Go to Contacts → Bulk Import. 3.Upload a CSV file containing contacts for: “Aravind Industries” & “AIL” 4.Verify the companies created after import. 5.Open the newly created “AIL” company profile. 6.Check the contacts associated with the “AIL” company. 7.Verify the contacts under “Aravind Industries.” | The system should associate contacts with their respective companies based on the company name provided in the CSV file | The system automatically creates the “AIL” company. No contacts are associated with the “AIL” company. The contact that belongs to “AIL” is incorrectly displayed under “Aravind Industries | https://drive.google.com/file/d/1GcaRcAfAKHnSvMthJCk7XufqCmNmAI7H/view?usp=drive_link | Aravinda Swamy | Open
DEF070 | Won Opportunities Not Reflecting in Dashboard Won Revenue | Dashboard | Medium | Medium | Functional | Won opportunities are not being reflected in the won revenue section on the dashboard | 1.Create a new opportunity 2.Mark the opportunity status as “Won” 3.Navigate to the Dashboard page 4.Check the “Won Revenue” section | The revenue from the won opportunity should be displayed in the dashboard’s won revenue section | The won opportunity revenue is not reflected in the dashboard | https://drive.google.com/file/d/1mkqTw6snta2hYmU83lPU20--ueAPhJKe/view?usp=drive_link | Aravinda Swamy | Open
DEF071 | Invitation sent toast message appears, but Pending Invitations list shows empty state | Tools-Team | High | Medium | Functional | "Invitation sent" success toast is displayed, but the Pending Invitations list remains empty and shows the empty state instead of the newly sent invitation | 1. Sign into Account 2. Click on "TOOLS"on Slidebar 3. Click on "Team" 4. Click on "Invite Member" 5. Enter Email and role 6. Click on Send Invite 7. Go to pending section and observe | "Invitation sent" toast and invitation appears in the pending list | "Invitation sent" toast message appeared but pending list is empty state | https://drive.google.com/file/d/101KzMWVFVGgQpb0pFhK8si_Nwl8LQL7w/view?usp=drive_link | Aravinda Swamy | Closed | Verified
DEF072 | Copy and Delete actions are not available during keyboard navigation | Inboundleads- Form builder | Medium | Medium | Accessibility | The Copy and Delete action buttons appear when interacting with the field using the mouse/cursor. However, when navigating to the same field using the keyboard (Tab key), these action buttons do not appear at all. As a result, keyboard users cannot discover or access these actions | 1. Go to Formbuilder 2. Select any fileds 3.Navigate through the page using the Tab key. 4.Move focus to the target field 5.Observe the available actions 6.Compare the behavior with mouse interaction over the same field | Copy and Delete buttons should become visible when the field receives keyboard focus, just as they do during mouse interaction. The buttons should be included in the keyboard focus order and be operable using Enter/Space keys. Visible focus indicators should be provided for keyboard users | Copy and Delete buttons appear only during mouse/cursor interaction. When the field receives keyboard focus, the buttons are not displayed. Users cannot access these actions using keyboard navigation | https://drive.google.com/file/d/1uYjlhXFYgkusxscbfKXqTIVwr5iUfj7Z/view?usp=drive_link | Aravinda Swamy | Open
DEF073 | Inventory Catalog Upload allows dupliacte files | Inbound Leads-Inventory | Medium | Medium | Validation | The file upload feature allows the same file to be uploaded multiple times without any duplicate detection or warning | 1.Navigate to Inventory Catalog module 2.Upload a XLSX/CSV file 3.Wait for the parsing process to complete 4. Again same file upload again 5.Observe uploaded files | The system should detect duplicate files and either: Prevent the duplicate upload, or Display a warning/confirmation message to the use | The same file can be uploaded multiple times, resulting in duplicate entries | https://drive.google.com/file/d/1sbBqq-PRXtJC6d3H__SzhkJWfAbzyTGB/view?usp=drive_link | Aravinda Swamy | Done by Shankar, open for review
DEF074 | Unable to Revoke Invitation – "Failed to revoke invitation" Error Message Displayed | Tools-Team | Medium | Medium | Functional | When attempting to revoke an invited user's invitation by clicking the Revoke action, the operation fails and an error message is displayed | 1.Navigate to the Team Module 2.Locate a pending invitation 3.Click the Revoke option under Actions 4.Observe the result | The invitation should be successfully revoked, removed from the pending invitations list (or updated accordingly), and a success message should be displayed | A toast notification is displayed with the message: "Failed to revoke invitation" The invitation remains active and is not revoked | https://drive.google.com/file/d/1qEAC6xoIHhpfbiyvFwGan8Te3jiq_xgT/view?usp=drive_link | Aravinda Swamy | Done by Santhosh: It is because admin can only revoke the invite, for manager only can sent. Now, I change the message to display correct message. | Admin need to review

## Product Enhancement Request
Module | Feature | Enhancement Request | Description | Priority | Status | Requested By
Companies | Edit Button | Add Edit option | Enable edit button inside Companies module to modify company details directly | High | Open | Raghav
Contacts | Edit Button | Add Edit option | Enable edit button inside Contacts module to modify contact details directly | High | Open | Raghav
CRM[Companies, Contacts, Opportunities, Activities] | Module Switch Dropdown | Add dropdown near Columns to switch between Companies, Contacts, Opportunities | Allow quick switching between CRM modules from table view | High | Open | Raghav
Campaigns | Recipient Source Breakdown | Separate Apollo and Outbound Leads recipients | Display recipient list and counts separately based on source (Apollo vs Outbound Leads) with drill-down view including name, email, source, and status | Medium-High | Open | Kannan
Campaigns | Lead Selection UI(SMart Filter) | Manual lead selection with source filter | Add side panel to view/select leads with dropdown filter (Apollo/HubSpot) | High | Open | Kannan
User Management / Team Members | User Activation Control | Add option to reactivate deactivated team members | Currently, once a team member is deactivated, there is no option available to reactivate the user. This restricts admins from restoring access and leads to duplicate account creation. The system should provide a “Reactivate” option for deactivated users, along with proper visibility (e.g., separate tab or filter) and confirmation action. | Medium | Open | Kannan